## Sprint Board
Task No. | Epic | User Story ID | User Story (Short) | Task | Assigned To | T-Shirt Sizing | Story Point | Estimate (hrs) | Status | Blocker / Notes | DoD Met?
1 | Auth | 1.1 | Splash screen | 1. Create splash screen component in react native 2. Add logo app name, tagline text 3. Add brand values text | Alekhya | XS | 1 |  | ToDo |  | No
4 | Auth | 1.1 | Splash screen | 1. Implement 3-second timer 2. Loading the required app resources within that span 3. Navigate to Landing screen after timer | Alekhya | S | 2 |  | ToDo |  | No
| Auth |  |  | Create reusable color palate | Anirban | XL | 8
| Auth |  |  | Create reusable fonts library | Sayan | L | 5
| Auth |  |  | Create reusable UI elements package | Anirban | XL | 8
6 | Auth | 1.2 | Landing Screen | 1. Create landing screen layout 2. Add Rent a Bike primary button 3. Add List a Bike primary button 4. Add Explore hyperlink | Alekhya | S | 2 |  | ToDo |  | No
10 | Auth | 1.2 | Landing Screen | Handle button press → store entry intent (Rent/List) | Anirban | M | 3 |  | ToDo |  | No
11 | Auth | 1.2 | Landing Screen | 1. Logged in renter should be navigated to RenterE-BikeBookingFilter screen 2. Logged in owner with zero listed e-bikes should be navigated to OwnerE-BikeListing screen 3. Logged in owner with existing listed e-bikes should be navigated to OwnerExistingE-BikesList screen | Anirban | M | 3 |  | ToDo |  | No
14 | Auth | 1.2 | Landing Screen | Unlogged in users should be navigated to SignIn screen upon pressing any button | Anirban | S | 2 |  | ToDo |  | No
15 | Auth | 1.2 | Landing Screen | Pressing on the explore hyperlink should navigate the user to ExploreMaps screen | Anirban | S | 2 |  | ToDo |  | No
16 | Auth | 1.3 | Sign in Screen | Create Sign In screen layout | Alekhya | XS | 1 |  | ToDo |  | No
17 | Auth | 1.3 | Sign in Screen | Add Email input field | Alekhya | XS | 1 |  | ToDo |  | No
18 | Auth | 1.3 | Sign in Screen | Add Password input field | Alekhya | XS | 1 |  | ToDo |  | No
19 | Auth | 1.3 | Sign in Screen | Add Continue button | Alekhya | XS | 1 |  | ToDo |  | No
20 | Auth | 1.3 | Sign in Screen | Add SignUp hyperlink | Alekhya | XS | 1 |  | ToDo |  | No
21 | Auth | 1.3 | Sign in Screen | Handle navigation from Landing → Sign In | Sayan | S | 2 |  | ToDo |  | No
22 | Auth | 1.3 | Sign in Screen | Preserve entry intent (Rent/List) | Sayan | S | 2 |  | ToDo |  | No
23 | Auth | 1.3 | Sign in Screen | 1. Client-side email match with database entry 2. Client-side password match with database entry 3. Disable Continue button on invalid input 4. Show inline validation errors | Sayan | XL | 8 |  | ToDo |  | No
27 | Auth | 1.3 | Sign in Screen | Create login API service with FastAPI | Sayan | L | 5 |  | ToDo |  | No
28 | Auth | 1.3 | Sign in Screen | Handle loading state | Anirban | M | 3 |  | ToDo |  | No
29 | Auth | 1.3 | Sign in Screen | Handle successful login response | Anirban | M | 3 |  | ToDo |  | No
30 | Auth | 1.3 | Sign in Screen | Handle invalid credentials error | Anirban | M | 3 |  | ToDo |  | No
31 | Auth | 1.3 | Sign in Screen | Detect entry intent (Rent/List) | Anirban | M | 3 |  | ToDo |  | No
32 | Auth | 1.3 | Sign in Screen | Detect user role (Owner/Renter) | Anirban | M | 3 |  | ToDo |  | No
33 | Auth | 1.3 | Sign in Screen | Navigate to RenterE-BikeBookingFilter screen | Anirban | S | 2 |  | ToDo |  | No
34 | Auth | 1.3 | Sign in Screen | Navigate to OwnerE-BikeListing or OwnerExistingE-BikesList screen | Anirban | S | 2 |  | ToDo |  | No
35 | Auth | 1.3 | Sign in Screen | Show personalized welcome note | Alekhya | XS | 1 |  | ToDo |  | No
36 | Auth | 1.3 | Sign in Screen | Set correct bottom nav tab | Anirban | M | 3 |  | ToDo |  | No
37 | Auth |  |  | Detect logged-in user state | Anirban | M | 3 |  | ToDo |  | No
38 | Auth |  |  | Handle Rent button press → RenterE-BikeBookingFilter screen | Anirban | M | 3 |  | ToDo |  | No
39 | Auth |  |  | Handle List button press → First time Listing? → OwnerE-BikeListing screen | Anirban | M | 3 |  | ToDo |  | No
40 | Auth |  |  | Handle List button press → Existing lister? → OwnerExistingE-BikesList screen | Anirban | M | 3 |  | ToDo |  | No
41 | Auth |  |  | Skip Sign In screen | Anirban | M | 3 |  | ToDo |  | No
42 | Auth |  |  | Preserve bottom navigation state: Owner: My Bikes Renter: my Rides | Anirban | M | 3 |  | ToDo |  | No
43 | Auth |  | Explore-guest | Create Explore screen shell | Alekhya | XS | 1 |  | ToDo |  | No
44 | Auth |  |  | Handle Explore link from Landing | Anirban | M | 3 |  | ToDo |  | No
45 | Auth |  |  | Handle Explore bottom nav selection | Anirban | M | 3 |  | ToDo |  | No
46 | Auth |  |  | Allow guest access | Anirban | M | 3 |  | ToDo |  | No
47 | Auth |  |  | Persist Explore tab selection | Anirban | M | 3 |  | ToDo |  | No
48 | Auth |  |  | Detect auth state on tab press | Anirban | M | 3 |  | ToDo |  | No
49 | Auth |  |  | Block navigation for My Rides | Anirban | M | 3 |  | ToDo |  | No
50 | Auth |  |  | Block navigation for My Bikes | Anirban | M | 3 |  | ToDo |  | No
51 | Auth |  |  | Block navigation for Profile | Anirban | M | 3 |  | ToDo |  | No
52 | Auth |  |  | Redirect to Sign In screen | Anirban | M | 3 |  | ToDo |  | No
53 | Auth |  |  | Preserve target tab intent | Anirban | M | 3 |  | ToDo |  | No
54 | Auth |  |  | After login → redirect to intended tab | Anirban | M | 3 |  | ToDo |  | No
55 | Auth |  | Sign Up Screen | 1. Create Sign Up screen layout 2. Full Name input 3. Birth date picker 4. Email input 5. Terms & Conditions checkbox 6. Disable Continue button until checkbox checked | Alekhya | L | 5 |  | ToDo |  | No
61 | Auth |  |  | Client-side validations: 1. Age > 16 years 2. Prevent using same email to signup twice 3. Name should match Govt. ID name | Anirban | L | 5 |  | ToDo |  | No
62 | Auth |  |  | Show inline errors | Alekhya | XS | 1 |  | ToDo |  | No
63 | Auth |  | SignUp-T&C | Create T&C screen | Alekhya | XS | 1 |  | ToDo |  | No
64 | Auth |  |  | Render scrollable content | Alekhya | S | 2 |  | ToDo |  | No
65 | Auth |  |  | Implement “OK” button | Alekhya | XS | 1 |  | ToDo |  | No
66 | Auth |  |  | Navigate back to Sign Up screen upon pressing OK button | Anirban | M | 3 |  | ToDo |  | No
67 | Auth |  | SignUp-ID Upload | Add ID upload button | Alekhya | S | 2 |  | ToDo |  | No
68 | Auth |  |  | Integrate camera/gallery picker | Anirban | M | 3 |  | ToDo |  | No
69 | Auth |  |  | Preview uploaded ID | Anirban | M | 3 |  | ToDo |  | No
70 | Auth |  |  | Validate file type | Anirban | M | 3 |  | ToDo |  | No
71 | Auth |  |  | Handle upload failure | Anirban | M | 3 |  | ToDo |  | No
72 | Auth |  | SignUp-Selfie | Add selfie capture button | Alekhya | XS | 1 |  | ToDo |  | No
73 | Auth |  |  | Open camera | Anirban | M | 3 |  | ToDo |  | No
74 | Auth |  |  | Capture selfie image | Anirban | M | 3 |  | ToDo |  | No
75 | Auth |  |  | Preview selfie | Anirban | M | 3 |  | ToDo |  | No
76 | Auth |  |  | Retake option | Anirban | M | 3 |  | ToDo |  | No
77 | Auth |  |  | 1. Validate image against ID ~ 80% 2. Validate image is without hats or glasses 3. Validate image clarity (no blur or shake) | Sayan | XL | 8 |  | ToDo |  | No
80 | Auth |  | SignUp-Backend | Create registration API service with FastAPI | Sayan | L | 5 |  | ToDo |  | No
81 | Auth |  |  | Submit form data | Anirban | M | 3 |  | ToDo |  | No
82 | Auth |  |  | Submit ID image | Anirban | M | 3 |  | ToDo |  | No
83 | Auth |  |  | Submit selfie image | Anirban | M | 3 |  | ToDo |  | No
84 | Auth |  |  | Show loading state | Anirban | M | 3 |  | ToDo |  | No
85 | Auth |  |  | Handle backend validation errors (existing email) | Anirban | M | 3 |  | ToDo |  | No
86 | Auth |  |  | Display field entry errors | Alekhya | S | 2 |  | ToDo |  | No
87 | Auth |  |  | Auto-login user upon successful sign up | Anirban | S | 2 |  | ToDo |  | No
88 | Auth |  |  | Detect entry intent (Rent/List) | Anirban | M | 3 |  | ToDo |  | No
89 | Auth |  |  | 1. Renter should be navigated to RenterE-BikeBookingFilter screen 2. Owner with zero listed e-bikes should be navigated to OwnerE-BikeListing screen 3. Owner with existing listed e-bikes should be navigated to OwnerExistingE-BikesList screen | Anirban | L | 5 |  | ToDo |  | No
90 | Auth |  |  | Show personalized welcome note | Alekhya | S | 2 |  | ToDo |  | No
91 | Auth
92 | Auth
93 | Auth
94 | Auth
95 | Auth
96 | Auth
97 | Auth
98 | Auth
99 | Auth

## Daily Standup Guide
Daily Standup Checklist
Is any task Blocked?
Is any task In Progress for >2 days?
Is Sprint Goal still safe?
Any dependency issues?
Any help needed today?

## Burndown
Day | Remaining Story Points
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
Day 8
Day 9
Day 10