## Sheet1
ID | User Story # | Sprint # | Type | Impediment | Details | Resolution | Owner | SME | Priority | Status | Note
1 | 1.1 |  | Ambiguity | Logo image file. | We have a logo of Micro2Move in \Micro2Move\Micro2Move Branding.pdf file. Will we take screen print of the .pdf file and use the same as the logo in MVP? Will we have artwork designers for the main project? |  | Sayan | Aidan | Low | Open | We can take screen print from the .pdf file to be used as logo in the MVP phase.
2 | 1.1 |  | Ambiguity | Brand values for Splash Screen | Do we need to put in the brand values in the Splash screen? Do we put in only: "Affordable Reliable Safe"? Or we put in: * Accessibility & Affordability * Sustainability & Climate Action * Safety & Reliability * Community & Local Empowerment |  | Sayan | Aidan | Low | Open | We can use: Affordable Reliable Safe
3 | 1.1 |  | Ambiguity | Splash Screen Carousel | Do we really need carousel of images for splash screen? This is not a good practice. Only the logo and few small text is the best practice. In case we really need to do, what will be the actual image files? Otherwise, max, we can use one fixed image in the splash screen (depricated). We need that image file in that case. |  | Sayan | Aidan | Low | Open | For MVP we can create the temporary logo image here. We can get a proper artwork in the production phase.
4 | 1.2 |  | Ambiguity | Landing page branding | The landing page (with Rent a Bike button, List a Bike button and Explore link) has some branding image. What image files could be used for the same? |  | Sayan | Aidan | Low | Open | For MVP we are reusing the logo here. We can get a proper artwork in the production phase.
5 | Generic |  | Ambiguity | Color Scheme | The visual components in the Micro2Move Branding.pdf contains more colors and shades than provided in the Color Scheme section of the same. Do we generate the most tentative and apparent shades as required? |  | Sayan | Aidan | Low | Open | We can easily generate the #RGB values as required at least during the MVP stage. We will use soft-coding schemes such that the final color schemes in the production app can be easily implemented when we have proper artist teams.
6 | 1.4 |  | Ambiguity | Login | Do we need Forget/ Change Password for MVP? |  | Sayan | Aidan | Low | Open | We suggest we do not need these features for MVP
7 | 1.4 |  | Ambiguity | Login | Do we need Google/ FaceBook/ Apple etc. based OAuth2 Authentication? |  | Sayan | Aidan | Low | Open | We suggest we do not need these features for MVP
8 | 1.4 |  | Ambiguity | Login | Do we need MFA Authentication? |  | Sayan | Aidan | Low | Open | We suggest we do not need these features for MVP
| 1.4 |  | Query | Renter Filter | What are the different categories of e-Bikes? Road Mountain City/Commuter Hybrid Cruiser Folding Fat-Tire Cargo |  | Sayan | Aidan | High | Open | Need this information to proceed
9 | 1.5 |  | Ambiguity | T&C | What is the exact purpose of the More Here link? |  | Sayan | Aidan | Low | Open | We can use the vertical scroll bar.
10 | 1.5 |  | Ambiguity | T&C | We need the exact legal documet for T&C. |  | Sayan | Aidan | Low | Open | For MVP, we can use technically Lorem Ipsum, but that will raise a few questions about our Risk Awareness. We can also use AI generated T&C list for MVP.
11 | 1.5 |  | Ambiguity | KYC validation | Do we only validate the selfie image vs the government ID image to be the same person? Or do we require other validations of the Govt ID, e.g. genuinity, expiry date, DoB, name match etc. |  | Sayan | Aidan | Low | Open | For MVP we can only validate the selfie image vs the government ID image to be the same person.
12 | 1.5 |  | Ambiguity | KYC validation | What is the accuracy % required to validate the selfie image vs the government ID image to be the same person? |  | Sayan | Aidan | Low | Open | For MVP 90% should be good. We may need to be > 99.0% for production.
13 | 1.5 |  | Ambiguity | Selfie validation | Do we validate against the selfie wearing dark glasses or hat? What error messages do we put in for a negative validation in this case? |  | Sayan | Aidan | Low | Open | We keep this features only in production and assume user does not wear dark glasses or hats while taking selfie during MVP
14 | 1.5 |  | Ambiguity | Create password verification | Do we keep Password Confirmation while registering in MVP? |  | Sayan | Aidan | Low | Open | We suggest we do not need these features for MVP
15 | 1.5 |  | Ambiguity | Hide/ Show password | Do we Hide/ Show password in Login/ Register in MVP? |  | Sayan | Aidan | Low | Open | We suggest we do not need these features for MVP
16 | Generic |  | Ambiguity | Light/ Dark Modes/ Themes | Will we consider Light/ Dark modes or Color Themes in MVP? |  | Sayan | Aidan | Low | Open | We suggest we do not need these features for MVP
17 | 1.10 |  | Ambiguity | Sign Up | Do we validate that the user's age is above or equal to 16 while registration (sign up) process? |  | Sayan | Aidan | Low | Open
18 | 1.11 |  | Ambiguity | Sign Up | Do we validate that the user's age matches the KYC document's age while registration (sign up) process? |  | Sayan | Aidan | Low | Open
2 |  |  |  | The button itself serves no purpose other than adding an extra click, shall we remove it and put List a bike, Rent a bike and Explore buttons there, keeping better UX in mind? | Get Started button's purpose |  | Sayan |  | Medium | Open | Dev suggestion. Subject to discussion.