## Sprint Board
Task # | Epic | User Story ID | User Story (Short) | Scope | Task | Assigned To | T-Shirt Sizing | Story Point | 102 | 16 | Status | Blocker / Notes | DoD Met?
12 | Marketplace-Renting | 1.1 |  | Test |  | Atish |  |  |  | 16 | ToDo |  | No
13 | Marketplace-Renting | 1.1 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
14 | Marketplace-Renting | 1.1 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
15 | Marketplace-Renting | 1.1 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
16 | Marketplace-Renting | 1.1 |  | Test |  | Atish |  |  |  |  | ToDo
17 | Marketplace-Renting | 1.1 |  | Test |  | Atish |  |  |  |  | ToDo
18 | Marketplace-Renting | 3.1 | RenterE-BikeBookingFilter | Frontend Dev | In RenterE-BikeBookingFilter screen component/layout: 1. Heading: "Welcome username" 2. Subheading: "Book an E-Bike" 3. From DatePicker and To DatePicker 4. Price Range (per week) 5. Category box with dropdown for bike types 6. Pickup Location - Location Picker 7. Style Continue button as primary 8. Style Visit My Bookings button as secondary 9. Navigate from RenterE-BikeBookingFilter → RenterE-BikeBooking-BikeDetails on Continue button press 10. Navigate from RenterE-BikeBookingFilter → RenterBookedBikesList on Visit My Bookings button press | Alekhya | L | 5 | 5 |  | ToDo |  | No
| Marketplace-Renting | 3.1 | RenterE-BikeBookingFilter | Frontend Dev | 1. Accept filter values from RenterE-BikeBookingFilter screen 2. Fetch / mock list of available e-bikes 3. Apply filters to e-bike dataset 4. Sort matching bikes in ascending order of price 5. Identify cheapest bike from filtered results 6. If no results, show message: “No E-Bikes found! Consider increasing your budget.” | Alekhya | S | 2 | 2
| Marketplace-Renting | 3.1 | RenterE-BikeBookingBikeDetails | Frontend Dev | 1. Create RenterE-BikeBooking-BikeDetails screen component/layout: 2. Render an empty card for highlighting the cheapest e-bike 3. Price, E-bike type, pickup location, Date placeholders under big card 4. Style Book This E-Bike button as primary 5. Add Subheading: Similar E-Bikes under the button | Alekhya | S | 2 | 2
| Marketplace-Renting | 3.1 | RenterE-BikeBookingBikeDetails | Frontend Dev | 1. Render the cheapest E-Bike's - enlarged image as the card's background image (occupying 100% of the card) - name, rating with (no. of ratings) in the lowest sub-section of the card with 85% opacity. 2. Price, E-bike type, Pickup location, Date of the cheapest e-bike under the card 3. Wire Book This E-Bike button to the highlighted bike | Alekhya | S | 2 | 2
|  |  | RenterE-BikeBookingBikeDetails | Frontend Dev | 1. Design the cards for Similar E-Bikes list of cards 2. Make the cards clickable 3. Render E-bike name, Circular thumbnail of the E-Bike, rating, Date Range, Price, E-bike type, Pickup location in the cards | Alekhya | S | 2 | 2
| Marketplace-Renting | 3.1 | RenterE-BikeBookingBikeDetails | Frontend Dev | 1. Render remaining bikes as list of clickable cards, under Similar E-Bikes subheading 2. Ensure list order: cheapest → costliest 3. Ensure scrollable list behavior 4. Handle loading state (skeleton) 5. Detect no-results condition 6. If no more filtered matching bikes to show in the Similar E-Bikes list: - Display: "Increase your budget to discover more amazing E-Bikes!" - Disable scroll of the list view | Alekhya | M | 3 | 3
20 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
21 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
22 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
23 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
24 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
25 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
26 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
29 | Marketplace-Renting | 3.2 |  | Test |  | Atish |  |  |  |  | ToDo |  | No
32 | Marketplace-Renting | 3.2 | RenterE-BikeBookingConfirmation | Frontend Dev | 1. Capture selected bike ID on click of Book This E-Bike Button or cards from the list 2. Navigate to RenterE-BikeBookingConfirmation screen 3. Pass selected bike details via navigation params 4. Render selected bike details on RenterE-BikeBookingConfirmation screen | Alekhya | XS | 1 | 1 |  | ToDo |  | No
| Marketplace-Renting | 3.2 | RenterE-BikeBookingConfirmation | Frontend Dev | Create RenterE-BikeBookingConfirmation screen component/layout: 1. Render the selected E-Bike's - enlarged image as the card's background image (occupying 100% of the card) - name, rating with (no. of ratings) in the lowest sub-section of the card with 85% opacity. 2. Price, E-bike type, Pickup location, Date range of booking (From-To) of the cheapest e-bike under the card 3. View Owner's Profile clickable hyperlink 4. Insurance Requirements section with 2-3 lines of the document, ending with Learn More hyperlink 5. A chcekbox with "Purchase mandatory Insurance" (Insurance is hyperlink) 6. A primary button Book | Alekhya | XS | 1 | 1
1. View Owner's Profile onClick navigate to RenterE-BikeBooking-SelectedBike'sOwnerDetails screen 2. Learn More and Insurance hyperlink onClick navigate to RenterE-BikeBookingInsuranceDetails screen 3. Disable onClick of Book button until checkbox is not checked 4. If checked, onClick Book button navigate to RenterBookedE-BikesList screen
33 | Auth | 1.3 | Sign In | Test |  | Alekhya | M | 3 | 3 |  | ToDo |  | No
34 | Auth | 1.3 | Sign In | Test |  | Atish | XS | 1 | 1 |  | ToDo |  | No
36 | Auth | 1.3 | Sign In | Test |  | Atish | S | 2 | 2 |  | ToDo |  | No
38 | Auth | 1.3 | Sign In | Test |  | Atish | XS | 1 | 1 |  | ToDo |  | No
39 | Auth | 1.3 | Sign In | Test |  | Atish | S | 2 | 2 |  | ToDo |  | No
40 | Auth | 1.3 | Sign In | Frontend Dev |  | Alekhya | L | 5 | 5 |  | ToDo |  | No
41 | Auth | 1.3 | Sign In | Frontend Dev | [6 empty] | ToDo |  | No
43 | Auth | 1.3 | Sign In | Frontend Dev | [6 empty] | ToDo |  | No
44 | Auth | 1.3 | Sign In | Frontend Dev | [6 empty] | ToDo |  | No
45 | Auth | 1.3 | Sign In | Frontend Dev | [6 empty] | ToDo |  | No
46 | Auth | 1.3 | Sign In | Frontend Dev | [6 empty] | ToDo |  | No
47 | Auth | 1.3 | Sign In | Frontend Dev | [6 empty] | ToDo |  | No
48 | Auth | 1.3 | Sign In | Frontend Dev | You do not have an active booking for these dates! | [5 empty] | ToDo |  | No
49 |  | 1.4 | Post-landing Navigation | Test | Given user's authStatus = AUTHENTICATED, pressing Rent a Bike button: 1. Navigates to RenterE-BikeFilter screen 2. Activates My Rides bottomNavTab | Atish | S | 2 | 2 |  | ToDo |  | No
50 |  | 1.4 | Post-landing Navigation | Test | Given user's authStatus = AUTHENTICATED, pressing List a Bike button: 1. Navigates to OwnerE-BikeListing screen 2. Activates My Bikes bottomNavTab | [5 empty] | ToDo |  | No
51 |  | 1.4 | Post-landing Navigation | Test | Given user's authStatus = UNAUTHENTICATED, pressing Rent a Bike or List a Bike button navigates to SignIn page | [5 empty] | ToDo |  | No
52 |  | 1.4 | Post-landing Navigation | Test | Pressing Explore hyperlink 1. Navigates to ExploreMaps screen layout (MANUAL/e2e TESTING) 2. Activates Explore bottomNavTab (MANUAL/e2e TESTING) | [5 empty] | ToDo |  | No
53 |  | 1.4 | Post-landing Navigation | Frontend Dev | Given user's authStatus = AUTHENTICATED and entryIntent = RENT: 1. Navigate to RenterE-BikeFilter screen 2. Show "Welcome Username" as heading of the RenterE-BikeFilter screen 3. Show "Book an E-Bike" sub-heading under heading 3. Activate My Rides bottomNavTab | Alekhya | M | 3 | 3 |  | ToDo |  | No
54 |  | 1.4 | Post-landing Navigation | Frontend Dev | Given user's authStatus = AUTHENTICATED and entryIntent = LIST: 1. Navigate to OwnerE-BikeBooking screen 2. Show "Welcome Username" as heading of the OwnerE-BikeListing screen 3. Show "Your E-Bikes" as subheading under heading 4. Activate My Bikes bottomNavTab | [5 empty] | ToDo |  | No
55 |  | 1.4 | Post-landing Navigation | Frontend Dev | Given user's authStatus = UNAUTHENTICATED and entryIntent = LIST/RENT/NULL 1. Navigate to SignIn screen | [5 empty] | ToDo |  | No
56 | Auth | 1.4 | Post-landing Navigation | Frontend Dev | Given user's authStatus = AUTHENTICATED or UNAUTHENTICATED: 1. Navigate to ExploreMaps screen layout 2. Activate Explore bottomNavTab (guest access) | [5 empty] | ToDo |  | No
57 |  | 1.5 | Explore | Test | 1. Explore screen render 2. My Rides, My Bikes, Explore, Profile bottomNavTabs render with Explore tab active (MANUAL/e2e TESTING) | Atish | M | 3 | 3 |  | ToDo |  | No
58 |  | 1.5 | Explore | Test | All tab icons press call mockFunction() | [5 empty] | ToDo |  | No
59 |  | 1.5 | Explore | Test | If user's authStatus = UNAUTHENTICATED 1. My Rides, My Bikes, Profile tabs are not pressable (MANUAL/e2e TESTING) 2. user is navigated to SignIn screen (MANUAL/e2e TESTING) | [5 empty] | ToDo |  | No
60 |  | 1.5 | Explore | Test | If user's authStatus = UNAUTHENTICATED Routing logic works with tabs mapped to correct screens: 1. My Rides - RenterE-BikeFilter 2. My Bikes - OwnerE-BikeListing 3. Explore - ExploreMaps 4. Profile - Profile (MANUAL/e2e TESTING) | [5 empty] | ToDo |  | No
61 | Auth | 1.5 | Explore | Frontend Dev | Given user's authStatus = UNAUTHENTICATED, if user presses any other tab 1. Block navigation for My Rides, My Bikes, Profile 2. Store tab pressing intent of user in context tabIntent = RIDES, BIKES, PROFILE and share globally 3. navigate the user to SignIn screen | Alekhya | M | 3 | 3 |  | ToDo |  | No
62 | Auth | 1.5 | Explore | Frontend Dev | After successful login (if user's authStatus = AUTHENTICATED) redirect to the intended tab, based on tabIntent | Alekhya | M | 3 | 3 |  | ToDo |  | No
63 | Auth | 1.5 | Explore | Frontend Dev | Given user's authStatus = AUTHENTICATED, tapping on My Rides, My Bikes, Profile tabs should navigate the user to the respective screens | Alekhya | S | 2 | 2 |  | ToDo |  | No
64 | Auth | 1.6 | Sign Up | Test | Sign Up screen renders 1. Full Name input field is visible 2. Date of Birth input field and calendar control is visible 3. Email input is visible 4. Create Password input is visible 5. I accept the T&C checkbox is visible 6. Upload Government ID & Selfie buttons are visible 7. Continue button is visible 8. Sign In hyperlink is visible | Atish | XS | 1 | 1 |  | ToDo |  | No
65 | Auth | 1.6 | Sign Up | Test | 1. T&C checkbox pressing calls a mockFunction() 2. Govt. ID & Selfie buttons pressing calls a mockFunction() 3. Continue & Sign In pressing calls a mockFunction() | Atish | XS | 1 | 1 |  | ToDo |  | No
66 | Auth | 1.6 | Sign Up | Test | 1. T&C screen navigation and reverse navigation to Sign Up screen via Ok button works 2. Camera open, close, Retake, Ok navigations work 3. Sign In navigates to Sign In screen (MANUAL/e2e TESTING) | Atish | XS | 1 | 1 |  | ToDo |  | No
68 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Create Sign Up screen layout 2. Full Name input 3. Birth date picker - calendar control 4. Email input 5. Terms & Conditions checkbox 6. Disable Continue button until checkbox checked | Alekhya | M | 3 | 3 |  | ToDo |  | No
69 | Auth | 1.6 | Sign Up | Frontend Dev | Client-side validations: 1. Age > 16 years 2. Prevent using same email to signup twice | Anirban | M | 3 | 3 |  | ToDo |  | No
70 | Auth | 1.6 | Sign Up | Frontend Dev | Show inline errors | Alekhya | XS | 1 | 1 |  | ToDo |  | No
71 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Create T&C screen layout 2. Render scrollable content 3. Implement OK button 4. Navigate back to Sign Up screen upon pressing OK button | Alekhya | S | 2 | 2 |  | ToDo |  | No
76 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Submit form data 2. Submit ID image 3. Submit selfie image | Alekhya | L | 5 | 5 |  | ToDo |  | No
77 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Show loading state 2. Handle backend validation errors (existing email) 3. Display field entry errors | Alekhya | M | 3 | 3 |  | ToDo |  | No
78 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Auto-login user upon successful sign up 2. Do not let the user to continue until all details are filled and T&C is checked | Alekhya | XS | 1 | 1 |  | ToDo |  | No
79 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Detect entryIntent (RENT/LIST) 2. Detect tabIntent (RIDES/BIKES/PROFILE) | Alekhya | XS | 1 | 1 |  | ToDo |  | No
80 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Renter should be navigated to RenterE-BikeBookingFilter screen layout 2. Show "Welcome Username" as heading of the RenterE-BikeFilter screen 3. Show "Book an E-Bike" sub-heading under heading 4. Activate My Rides bottomNavTab | Alekhya | M | 3 | 3 |  | ToDo |  | No
81 | Auth | 1.6 | Sign Up | Frontend Dev | 1. Lister/Owner should be navigated to OwnerE-BikeBooking screen 2. Show "Welcome Username" as heading of the OwnerE-BikeListing screen 3. Show "Your E-Bikes" as subheading under heading 4. Activate My Bikes bottomNavTab | Alekhya | S | 2 | 2 |  | ToDo |  | No
67 | Auth | 1.7 | KYC | Test | 1. ID and Selfie matching accuracy ~ 80% (MANUAL/e2e TESTING) 2. Sign up attempt with duplicate email does NOT work 3. Sign up attempt with password length less than 6 characters does NOT work 4. Sign up attempt without checking in the T&C checkbox does not work | Atish | XS | 1 | 1 |  | ToDo |  | No
72 | Auth | 1.7 | KYC | Frontend Dev | 1. Add ID upload button 2. Integrate camera 3. Preview uploaded ID 4. Handle upload failure 5. Ok and Retake buttons 6. Ok button closes the camera and navigates to Sign Up screen, Retake button reopens the camera | Alekhya | XL | 8 | 8 |  | ToDo |  | No
73 | Auth | 1.7 | KYC | Frontend Dev | 1. Add selfie capture button 2. Open camera 3. Capture selfie image 4. Preview selfie 5. Ok and Retake buttons 6. Ok button closes the camera and navigates to Sign Up screen, Retake button reopens the camera 7. Handle upload failure | Alekhya | L | 5 | 5 |  | ToDo |  | No
74 | Auth | 1.7 | KYC | Frontend Dev | 1. Validate image against ID ~ 80% | Sayan | XL | 8 | 8 |  | ToDo |  | No
75 |  | 1.7 | KYC | Frontend Dev | 1. Validate image is without hats or glasses 2. Validate image clarity (no blur or shake) | Sayan | L | 5 | 5 |  | ToDo |  | No
82 | Auth
83 | Auth
84 | Auth
85 | Auth
86 | Auth

## Sheet1
Days | Actual Story Points Left | Expected Story Points Left | Story Points Done
0 | 156 | 156 | 0
1 | 156 | 140.4 | 0
2 | 156 | 124.8 | 0
3 | 156 | 109.2 | 0
4 | 156 | 93.6 | 0
5 | 148 | 78 | 8
6 | 148 | 62.4
7 | 148 | 46.8
8 | 148 | 31.2
9 | 148 | 15.6
10 | 148 | 0

## Daily Standup Guide
Daily Standup Checklist
Is any task Blocked?
Is any task In Progress for >2 days?
Is Sprint Goal still safe?
Any dependency issues?
Any help needed today?

## Burndown
Day | Remaining Story Points
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
Day 8
Day 9
Day 10