## Sprint Board
Epic | User Story ID | User Story (Short) | Scope | Task | Assigned To | T-Shirt Sizing | Story Point | 12 | 12 | Status | Blocker / Notes | DoD Met?
Explore | 4.1 | [6 empty] | 0 | 2 | ToDo |  | No
| 4.1 | [6 empty] | 0 |  | ToDo |  | No
| 4.1 | [6 empty] | 0 |  | ToDo |  | No
| 4.1 | [8 empty] | ToDo |  | No
| 4.1 | [6 empty] | 0 |  | ToDo |  | No
| 4.1 |  | Frontend Tasks | 1. Integrate google maps API to render map 2. Render 4 hyperlink variant buttons for: Maps, Info, Community Update, Ask AI 3. Searching destination from starting point (google maps native navigation feature) - Ask for user location - If user denies location, navigate to info option. Send an Alert: "location permission denied. Enable location for micro2move to access maps" 4. Integrate a toggle opening button for More options 5. Link More to open filters: Current charging stations, Future charging stations, Dedicated bike stations, bike lane infarstructure 6. Filters display respective points on map | Alekhya | S | 2 | 2 |  | ToDo |  | No
| 4.1 | [8 empty] | ToDo |  | No
| 4.1 | [8 empty] | ToDo |  | No
| 4.1 | [8 empty] | ToDo |  | No
| 4.1 | [8 empty] | ToDo |  | No
[9 empty] | 1 | ToDo |  | No
[10 empty] | ToDo |  | No
| 4.2 |  |  | 1. Render info screen, connect navigation with info hyperlink 2. Render static data in polished UI (approach TBD) 3. Highlight info option |  | XS | 1 | 1 |  | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 0 | ToDo
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 1 | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
| 4.3 |  |  | 1. Render Community Updates screen, connect navigation with Community Updates hyperlink 2. Render static data in polished UI (approach TBD) 3. Highlight Community Updates option |  | XS | 1 | 1 |  | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 0 | ToDo
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 2 | ToDo
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
ToDo
| 4.4 |  |  | 1. Render Ask AI screen, connect navigation with Ask AI hyperlink 2. Render static data in polished UI (approach TBD) 3. Highlight Ask AI option 4. Integrate Generative AI API for chat |  | S | 2 | 2 |  | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 0 | ToDo
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 2 | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
| 5.1 |  |  | 1. Render the profile screen layout, wire it with profile bottomnavtab. 2. Render "Welcome Username" as heading variant of label component 3. Render user's profile picture. - render edit option, integrate CameraPicker component 4. Render user's Name and Email 5. Render Bikes Rented section, displaying the no. of bikes rented by the user 6. Render Joined micro2move on section, displaying joining date of the user 7. Render Community Activity hyperlink variant button 8. Render In-App Lessons hyperlink variant button 9. Render Logout primary variant button - add local styling: {backgroundColor: Colors.Red} |  | S | 2 | 2 |  | ToDo
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 2 | ToDo
[10 empty] | ToDo |  | No
[6 empty] | S | 2 | 2 |  | ToDo |  | No
[9 empty] | 1 | ToDo |  | No
ToDo
ToDo
[10 empty] | ToDo |  | No
| 5.2 |  |  | 1. render Community Activity screen layout - Wire the screen with Community Activity hyperlink 2. Render static data in the screen |  | XS | 1 | 1 |  | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 0 | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 1 | ToDo |  | No
ToDo
ToDo
| 5.3 |  |  | 1. render In-App Lessons screen layout - Wire the screen with In-App Lessons hyperlink 2. Render static data in the screen |  | XS | 1 | 1 |  | ToDo |  | No
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No
[9 empty] | 0 | ToDo
[10 empty] | ToDo |  | No
[10 empty] | ToDo |  | No

## Burndown
Days | Actual Story Points Left | Expected Story Points Left | Story Points Done
0 | 115 | 115 | 0
1 | 115 | 115 | 0
2 | 115 | 115 | 0
3 | 115 | 115 | 0
4 | 115 | 0 | 0
5 | 115 | 0 | 0
6 | 115 | 0 | 0
7 | 115 | 0 | 0
8 | 115 | 0 | 0
9 | 115 | 0 | 0
10 | 115 | 0 | 0
Bur

## Daily Standup Guide
Daily Standup Checklist
Is any task Blocked?
Is any task In Progress for >2 days?
Is Sprint Goal still safe?
Any dependency issues?
Any help needed today?

## Ambiguities
User Story ID | Type | Impediments | Details | Resolution | Owner | SME | Priority | Status | Issue in | Solving Suggestion